## Slide 1
Risk Management Overview

## Slide 2: Risk Management Overview
What is Risk?
What is Risk Management?
The Crowe Framework
  Organisational Perspectives
  Principals
  Approach
  Process
  Embedding & Reviewing
  Risk Documents
  Common Techniques
  Health Check & Maturity Model
Agenda

## Slide 3: Risk Management Overview
Risk is defined as……
“An uncertain event or set of events that, should it occur, will have an effect on the achievement of objectives. A risk is measured by the combination of the probability of a perceived threat or opportunity occurring and the magnitude of its impact on objectives”
What is Risk?

## Slide 4: Risk Management Overview
The systematic application of principals, an approach, and a process applied to the tasks of identifying and assessing risks, and the subsequent planning and implementation of risk responses. This provides a disciplined environment for proactive decision-making.
For Risk Management to be effective, risks need to be:
  Identified
  Assessed
  Controlled
What is Risk Management?

## Slide 5: Risk Management Overview
For Risk Management to be effective, risks need to be:
  Identified: Considering uncertainties that would affect the achievement of objectives within the context of a particular organisational activity, and then describing/communicating them in order to ensure a common understanding
  Assessed: Estimating the probability, impact and proximity of individual risks so they can be prioritised. Understanding the overall level of risk (risk exposure) associated with the organisational activity
  Controlled: Planning appropriate responses to risks, assigning owners and actionees. Implementing, monitoring and controlling these responses
What is Risk Management?

## Slide 6: Risk Management Overview
Based on four core concepts:
  Principals
  Approach
  Process
  Embedding and Reviewing
The Crowe Framework

## Slide 7: Risk Management Overview
The Crowe Framework

## Slide 8: Risk Management Overview
Applying Principals, Approach and Process according to Organisational perspective:
  Strategic
  Programme
  Project
  Operational
Organisational Perspectives

## Slide 9: Risk Management Overview
Strategic
  Concerned with ensuring overall business success, vitality and viability
  Sets the scene for the management of risk across the entire organisation
  Information flows should be established between those with strategic responsibility and those with operational and programme responsibility
  Establish information flows with those with project responsibilities if project outputs are of strategic importance.
Organisational Perspectives

## Slide 10: Risk Management Overview
Programme
  Concerned with transforming business strategy into new ways of working that deliver measurable benefits to the organisation viability
  Sets the scene for the management of risk within the programme, and the projects and operational activities that form part of the programme
  Information flows should be established between those with programme responsibility and those with project responsibilities within the programme
  Establish information flows with those with operational responsibilities if the programme has an impact on these or vice-versa
Organisational Perspectives

## Slide 11: Risk Management Overview
Project
  Concerned with delivering defined outputs to an appropriate level of quality within agreed scope, time and cost constraints
  Sets the scene for the management of risk within the project
  Information flows should be established as required if the project supports strategic, programme or operational objectives
Organisational Perspectives

## Slide 12: Risk Management Overview
Operational
  Concerned with maintaining appropriate levels of business services to existing and new customers
  Sets the scene for the management of risk within particular operational (service delivery) areas
  Information flows need to be established between those with operational responsibilities, and those with strategic, programme and project responsibilities where any or all of these will have an impact on the operational area or vice-versa
Organisational Perspectives

## Slide 13: Risk Management Overview
Organisational Perspectives

## Slide 14: Risk Management Overview
Effective Risk Management satisfies the following eight principals:
  Aligns with objectives
  Fits the context
  Engages stakeholders
  Provides clear guidance
  Informs decision-making
  Facilitates continual improvement
  Creates a supportive culture
  Achieves measurable value
Management of Risk Principals

## Slide 15: Risk Management Overview
Aligns with Objectives:
  Consider the objectives from each of the four organisation perspectives
  Determine Risk Capacity & Risk Appetite for each of the four organisational perspective
  Remember that objectives can change, as such Risk Management is dynamic not static and is therefore a repetitive process
Management of Risk Principals

## Slide 16: Risk Management Overview
Fits the Context:
  External
    Sector, Markets, Locations, Technologies, Regulatory Regimes
  Internal
    Culture, Organisational Structure, Stakeholder Relationships
  Remember that context can change, as such Risk Management is dynamic not static and is therefore a repetitive process
  Designing the Risk Management Approach such that it can be applied to different & changing context, dealing effectively with risks, while at the same time, avoiding wasted effort/money
Management of Risk Principals

## Slide 17: Risk Management Overview
Engages Stakeholders:
  Adopt an appropriate level and style of communication
  Understand Stakeholder perception of risks
  Establish a common language/terminology
  Proactive and timely involvement
  Stakeholder Analysis
    Influence/Interest matrix
    RACI diagram
Management of Risk Principals

## Slide 18: Risk Management Overview
Provides Clear Guidance:
  Establish clear practices
  Apply practices coherently across all parts of the organisation
  Ensure consistency of information flows across organisational perspectives
Management of Risk Principals

## Slide 19: Risk Management Overview
Informs Decision Making:
  Help decision-makers understand the relative merits, threats, and opportunities associated with alternative courses of action
  Establish Roles & Responsibilities
  Establish Reporting & Escalation arrangement
  Define Risk Tolerance
  Establish Key Performance Indicators (KPI’s)
Management of Risk Principals

## Slide 20: Risk Management Overview
Facilitates Continual Improvement:
  Collecting actual performance data about how risks were identified, assessed and controlled, forms the basis for historical reference, allowing an organisation to learn from experience
  Establish a thorough system of internal control
    Risk Health Check
    Risk Maturity Model
Management of Risk Principals

## Slide 21: Risk Management Overview
Create a Supportive Culture:
  Organisation must recognise that managing risk appropriately means taking calculated chances
  Zero risk is neither possible nor desirable. A tolerable level of risk that matches the appetite for the organisational activity is needed
  Embedding of Risk Management into everyone’s day-to-day activities
  Open and honest discussion without fear of retribution
  Recognition and reward for managing risk proactively
Management of Risk Principals

## Slide 22: Risk Management Overview
Achieves Measurable Value:
  Establish baselines and processes to measure and track performance over time
  Examples
    Reduces waste and re-work
    Increases customer/client/user confidence
    Improves regulatory performance
    Improves levels of Health & Safety
Management of Risk Principals

## Slide 23: Risk Management Overview
The way in which Risk Principals are implemented
Centred around a set of key documents
Management of Risk Approach

## Slide 24: Risk Management Overview
Key documents
  Risk Management Policy
  Risk Management Process Guide
  Risk Strategy
  Risk Register
  Issue Register
  Risk Improvement Plan
  Risk Communications Plan
  Risk Response Plan
  Risk Progress Report
Management of Risk Approach

## Slide 25: Risk Management Overview
Risk Management Policy
  States why and how Risk Management will be implemented throughout an organisation
  Communicates in a common language
  Strives to establish uniformity across the Risk Management process and remove ambiguity about the organisation’s overall risk capacity, appetite and tolerance levels
  Describes the format and timing of reporting
  Subject to review on an annual basis and/or as a reaction to new legislation or government guidance
Management of Risk Approach

## Slide 26: Risk Management Overview
Risk Management Process Guide
  Describes how the process steps (from Identify through to Implement) will be carried out in the organisation
  Designed for all types of activity across the organisation
  Compliance with the Process Guide is often one of the hurdles used to establish a satisfactory level of internal control
  Subject to review on an annual basis and/or as a reaction to new legislation or government guidance
Management of Risk Approach

## Slide 27: Risk Management Overview
Risk Management Strategy
  Describes the specific Risk Management activities that will be taken for a particular organisational activity
  Multiple strategies are commonly used across an organisation, reflecting the need to apply risk differently according to the activity being considered, while still reflecting the overall organisational Policy and Process Guide
  Outlines the Risk Appetite for an organisational activity
  Where appropriate, may relate to the OGC Gateway Review process for the public sector or alternative assurance and approval processes for the private sector
Management of Risk Approach

## Slide 28: Risk Management Overview
Risk Register
  Purpose is to capture and maintain information on all of the identified threats and opportunities relating to a specific organisational activity
  Provides a snapshot, at any point in time, of the identified risks for the organisational activity in question, the priority of each risk, the risk owner for each risk, and the response strategy chosen by each risk owner
  Should also record when each risk was closed and why
  Document should be subject to formal document and version control
Management of Risk Approach

## Slide 29: Risk Management Overview
Issue Register
  Purpose is to capture and maintain information on all of the identified issues that are happening now and require action
  Issues may have arisen from risks that had been identified, but not managed
  Issues that have been raised, may be causes of new risks
  Important to understand issues, and how they are related to, yet different from, risks
  Timely transfer of relevant information between the Risk Register and the Issue Register enhances the effectiveness of management processes
Management of Risk Approach

## Slide 30: Risk Management Overview
Risk Improvement Plan
  Purpose is to assist with embedding Risk Management into the culture of the organisation and to document planned improvements
  Provides a record of the current maturity level of Risk Management within the organisation, the targets that have been set, the time period within which each target should be achieved, and the planned mechanisms/method that will be used to achieve the desired results
  Describes what the organisation needs to do to deal with the common process barriers
Management of Risk Approach

## Slide 31: Risk Management Overview
Risk Communications Plan
  Describes how information will be distributed to, and received from, all relevant stakeholders of a particular organisational activity.
  May form part of a wider communication plan within the organisation
  Effective communication between stakeholders is a critical success factor for Risk Management, ensuring that risks are identified and assessed, and that suitable responses are planned and owned
Management of Risk Approach

## Slide 32: Risk Management Overview
Risk Response Plan
  Details specific plans for responding to a single risk or a linked set of risks
  Linked to the ‘risk response’ field of the Risk Register
  Useful where a particular risk (or linked set of risks) warrants a significant and resource-intensive response
  Important to maintain the link with the Risk Register as progress is made in order to preserve data integrity and clarity of current status
Management of Risk Approach

## Slide 33: Risk Management Overview
Risk Progress Report
  Provides regular progress information to management on risk management within a particular organisational activity
  Comments on the progress of planned actions and their effectiveness
  Reports trend analysis and reports performance against measures established to demonstrate the value of risk management activities
Management of Risk Approach

## Slide 34: Risk Management Overview
Relationship between Documents
  At an organisational level, a Risk Management Policy, a Risk Management Process Guide, and at least one Risk Management Strategy must exist
  Multiple Risk Registers and Issue Registers will exist with an organisation, and a way of ensuring that risks and issues are handled within the correct perspective is essential
  The Risk Improvement Plan has close links with the approach (Policy, Process Guide & Strategy) for the organisational activity in question and the organisation as a whole. Improvements must be co-ordinated across the organisation, with clear reporting of plans and progress, via the Risk Progress Report
Management of Risk Approach

## Slide 35: Risk Management Overview
Relationship between Documents
Management of Risk Approach

## Slide 36: Risk Management Overview
Management of Risk Process

## Slide 37: Risk Management Overview
Four primary steps
  Identify
  Assess
  Plan
  Implement
Carried-out in sequence
Repetitive in nature
Embed & Review embraces each step
Principals permeate each step
Management of Risk Process

## Slide 38: Risk Management Overview
Common barriers to the implementation of process
  Lack of organisational culture that appreciates the benefits of Risk Management
  Immature Risk Management practices
  Lack of resources and time
  Lack of policies, strategies and plans
  Lack of senior management sponsorship
  Lack of training, knowledge and clear guidance
  Lack of incentives for participation in Risk Management activities
Management of Risk Process

## Slide 39: Risk Management Overview
Communication is vital across the whole process
  Everyone must understand
    How the organisation’s Risk Capacity and Risk Appetite is expressed by Risk Tolerances for the work in question
    The Risk Policy, Risk Process and Risk Strategy relevant to their role
    The benefits of effective Risk Management and the potential implications if it is not done
Management of Risk Process

## Slide 40: Risk Management Overview
Communication is vital across the whole process
  Each level of management must actively seek and receive assurances about the management of risk within their control
  Procurement teams must ensure that risk ownership is clearly specified within contracts and service agreements
  Transferrable lessons must be communicated to anyone that can benefit from them
Management of Risk Process

## Slide 41: Risk Management Overview
Identify, Access, Plan and Implement process steps
Described in the following format
  Goals
  Inputs
  Outputs
  Techniques
  Tasks
Management of Risk Process

## Slide 42: Risk Management Overview
Identify can be split into two sub-processes
  Identify – Context
  Identify – Risks
Management of Risk Process

## Slide 43: Risk Management Overview
Identify - Context
  Goal is to obtain information about the planned activity and how it fits into the wider organisation. This will include understanding:
    What constraints are relevant to the activity
    Who the stakeholders are and what their objectives are
    Where the activity fits in relation to the organisational structure
    The organisation’s environment (industry, market, etc.)
    The organisation’s approach to Risk Management
Management of Risk Process

## Slide 44: Risk Management Overview
Management of Risk Process

## Slide 45: Risk Management Overview
Identify - Context
  Tasks
    Establish activity objectives
    Establish activity scope
    Clarify assumptions
    Discover completeness of information
    Carry-out Stakeholder Analysis
    Clarify Risk Management Approach
Management of Risk Process

## Slide 46: Risk Management Overview
Identify - Risks
  Goal is to identify the risks to the activity objectives with the aim of minimising threats and maximising opportunities. This will include:
    Identifying the threats and opportunities to the activity
    Preparing a Risk Register
    Preparing key performance indicators and early warning indicators
    Understanding the stakeholder’s perception of the identified risks
Management of Risk Process

## Slide 47: Risk Management Overview
Management of Risk Process

## Slide 48: Risk Management Overview
Identify - Risks
  Tasks
    Identify threats and opportunities
    Establish stakeholder agreement
    Review clarity and comprehensiveness
    Record information on a Risk Register
    Apply structure to the Risk Register using categories, groups, etc
    Identify early warning indicators for KPI’s
Management of Risk Process

## Slide 49: Risk Management Overview
Assess can be split into two sub-processes
  Assess – Estimate
  Assess – Evaluate
Management of Risk Process

## Slide 50: Risk Management Overview
Assess - Estimate
  Goal is to prioritise individual risks so that it is clear which risks are most important and more urgent. This will require an understanding of:
    The probability of each threat and opportunity
    The impact of each threat and opportunity
    The proximity of each threat and opportunity
Management of Risk Process

## Slide 51: Risk Management Overview
Management of Risk Process

## Slide 52: Risk Management Overview
Assess - Estimate
  Tasks
    Confirm risk descriptions are clear
    Assess Probability, Impact and Proximity
    Update the Risk Register
Management of Risk Process

## Slide 53: Risk Management Overview
Assess - Evaluate
  Goal is to understand the Risk Exposure posed by the net effect of the identified threats and opportunities when added together
Management of Risk Process

## Slide 54: Risk Management Overview
Management of Risk Process

## Slide 55: Risk Management Overview
Assess - Evaluate
  Tasks
    Build risk model
    “This involves making an assessment of the relationships between risks. Are risks correlated or not? If one risks occurs, what impact, if any, does this have on the probability, impact and proximity of other risks?”
Management of Risk Process

## Slide 56: Risk Management Overview
Plan
  Goal is to prepare specific management responses to the threats and opportunities that have been identified. Responses should seek to remove or reduce the threats, and maximise the opportunities. Attention to detail and good communication will ensure as far as possible, that the business is not taken by surprise when a risk actually materialises
Management of Risk Process

## Slide 57: Risk Management Overview
Management of Risk Process

## Slide 58: Risk Management Overview
Plan
  Tasks
    Plan responses and cost-justify them
    Record residual risk
    Identify organisational ownership
    Identify risk owners and risk actionees
    Identify and Assess any secondary risks
    Measure residual risk against risk tolerance
Management of Risk Process

## Slide 59: Risk Management Overview
Implement
  Goal is to ensure that the planned responses are implemented and monitored for their effectiveness, and to ensure that corrective action is taken where planned responses do not match expectations
Management of Risk Process

## Slide 60: Risk Management Overview
Management of Risk Process

## Slide 61: Risk Management Overview
Implement
  Tasks
    Executing, Monitoring & Controlling
    Update Risk Register
    Update early warning indictors for KPI’s
    Close risks
    Produce and distribute reports
Management of Risk Process

## Slide 62: Risk Management Overview
Why is it important?
  How an organisation manages risk is an expression of it’s core values and communicates to stakeholders it’s appetite for and attitude to risk taking
  An unmanaged approach to risk leads to reactive rather than pro-active decision making, undermining stakeholder confidence
Embedding & Reviewing

## Slide 63: Risk Management Overview
Embedding the Principals
  Use the Risk Health Check model to establish a benchmark
  Use the Risk Maturity model to assess and schedule improvement over time
Embedding & Reviewing

## Slide 64: Risk Management Overview
Demonstrate the value
  Use questionnaires to collect information from across the organisation, reporting on the positive trend over time as risk management becomes second nature
  All activity within an organisation has a cost. As such it can be quantified. The time and effort spent on reacting to risks that were not Identified, Assessed or Controlled, should show a decrease in cost to the organisation over time as risk management seeps into the culture of the business
Embedding & Reviewing

## Slide 65: Risk Management Overview
Common Barriers to success
  Lack of organisational culture that appreciates the benefits of Risk Management
  Immature Risk Management practices
  Lack of resources and time
  Lack of policies, strategies and plans
  Lack of senior management sponsorship
  Lack of training, knowledge, tools and techniques
  Lack of clear guidance for managers and staff
  Lack of incentives for participation in Risk Management activities
Embedding & Reviewing

## Slide 66: Risk Management Overview
Overcoming the Common Barriers to success
  Appoint a board member responsible for Risk Management across the organisation
  Include a review of key risks on the agenda of all board meetings
  Include Risk Management in the staff induction programme
  Include risk-related objectives in staff appraisal and development plans
  Include risk-related responsibilities in job descriptions
  Implement a formal scheme that rewards staff who identify risks (threats or opportunities) that have a potentially high impact on the organisation
Embedding & Reviewing

## Slide 67: Risk Management Overview
Securing Senior Management support
  Communicate appointment of board level sponsor
  Include risk-related objectives in senior management bonus scheme
  Include a review of risks on the agenda of all management meetings
  Ensure that roles and responsibilities are clear and that there is a well-understood path for escalation
  Provide regular reporting on risks and their potential impact
  Communicate successfully planned and implemented risk responses
Embedding & Reviewing

## Slide 68: Risk Management Overview
Opportunities for Review, Change and Improvement
  Changes in organisational structure
  Expansion of the organisation into new markets or geographical areas
  Acquisition of a new business
  Changes in legislation relating to the sectors in which the organisation operates
  As a response to a risk response that has gone badly wrong
  Inclusion into a review of Change Management activities
Embedding & Reviewing

## Slide 69: Risk Management Overview
Risk Documents

## Slide 70: Risk Management Overview
Risk Management Policy
Risk Management Process Guide
Risk Management Strategy
Risk Register
Issue Register
Risk Improvement Plan
Risk Communications Plan
Risk Response Plan
Risk Progress Report
Risk Documents

## Slide 71: Risk Management Overview
Risk Management Policy
  Describes why Risk Management is important to the organisation
  Describes the specific objectives served by formal implementation of Risk Management
  Responsibility of the Senior Management team within the organisation
Risk Documents

## Slide 72: Risk Management Overview
Risk Management Policy
  Typical sections include
    Introduction, Risk Appetite & Capacity, Risk Tolerance Thresholds
    Roles & Responsibilities, Escalation & Delegation
    Reference to the Risk Management Process Guide
    KPI’s & EWI’s, Reporting, Budgeting, Quality Assurance
    Review Frequency, Glossary of Terms
Risk Documents

## Slide 73: Risk Management Overview
Risk Management Process Guide
  Describes how an organisation intends to perform Risk Management
  Describes the roles and responsibilities of the people who perform risk-related tasks
  Responsibility of a named Senior Manager within the organisation, who may choose to delegate to a risk specialist
Risk Documents

## Slide 74: Risk Management Overview
Risk Management Process Guide
  Typical sections include
    Introduction
    Roles & Responsibilities
    Steps in the Process
    Tools & Techniques to the used
    Document Templates to be used
    Glossary of Terms
Risk Documents

## Slide 75: Risk Management Overview
Risk Management Strategy
  Describes how the Risk Management Policy and Risk Management Process Guide will be implemented for a specific organisational activity
  Responsibility of the manager of the specific organisational activity (e.g. Operations Manager, Project Manager)
Risk Documents

## Slide 76: Risk Management Overview
Risk Management Strategy
  Typical sections include
    Introduction
    Summary of the risk process, referencing the Risk Management Process Guide
    Tools & Techniques to be used (in more detail than in the Risk Management Process Guide)
    Format of the Risk & Issue Registers
    Roles & Responsibilities
    Scales to be used for estimating risk probability and impact
    Risk Categories to be used
    Budget required
    Timing of activities (review points)
    Glossary of Terms
Risk Documents

## Slide 77: Risk Management Overview
Risk Register
  Documents all of the risks that have been identified as having an impact of the objectives of the specific organisational activity
  Responsibility of the manager of the specific organisational activity (e.g. Operations Manager, Project Manager)
Risk Documents

## Slide 78: Risk Management Overview
Risk Register
  The following attribute fields are commonly found in a Risk Register
    Unique Identifier, Risk Category, Date Raised, Raised By
    Description, Probability, Impact, Expected Value, Proximity
    Response Option, Response Action
    Residual Probability, Residual Impact, Residual Expected Value, Residual Proximity
    Secondary Risks
    Action Status, Risk Status, Risk Owner, Risk Actionee
Risk Documents

## Slide 79: Risk Management Overview
Issue Register
  Documents all of the unplanned situations that are happening now and require management attention
  Issues can be problems, benefits, queries or change requests
  The Issue Register forms the link between the risk management and issue resolution processes
  Responsibility of the manager of the specific organisational activity (e.g. Operations Manager, Project Manager)
Risk Documents

## Slide 80: Risk Management Overview
Issue Register
  The following attribute fields are commonly found in an Issue Register
    Unique Identifier, Issue Type, Date Raised, Raised By
    Description, Severity, Priority,
    Action Required, Action Implementation Date, Action Status
    Issue Status
    Issue Owner
Risk Documents

## Slide 81: Risk Management Overview
Risk Improvement Plan
  Brings together all of the actions required to improve the way in which Risk Management is performed within the organisation or a subset of it
  As a minimum it should focus on improving the culture and the context within which Risk Management can add value
  Responsibility of the manager of the specific organisational activity (e.g. Operations Manager, Project Manager)
Risk Documents

## Slide 82: Risk Management Overview
Risk Improvement Plan
  Typical sections include
    Current Date (the date the improvement plan is agreed or the date that the existing behaviour is assessed and recorded)
    Category Group (the target group of individuals)
    Existing Behaviours (description of current behaviours being exhibited)
    Target Behaviours (description of preferred/target behaviours)
    Target Date
    Mechanisms (for making the improvement)
    Measurement
Risk Documents

## Slide 83: Risk Management Overview
Risk Communications Plan
  May be a separate document, or included as part of a wider communications plan for the organisational activity in question
  Responsibility of the manager of the specific organisational activity (e.g. Operations Manager, Project Manager)
Risk Documents

## Slide 84: Risk Management Overview
Risk Communications Plan
  Typical sections include
    Key information to be distributed (what needs to be communicated and when)
    Roles & Responsibilities (who will prepare and distributed the message, who will gather feedback?)
    Stakeholder Requirements (which individuals need to be issued with which information)
    Mechanisms (which channels will be used for communication)
    Feedback processing (how feedback will be gathered, processed, and acted upon)
    Activity Schedule (the timing and frequency of communications)
Risk Documents

## Slide 85: Risk Management Overview
Risk Response Plan
  Is an extension of the Risk Register that provides more detail on the planned response.
  It is vital that version control between the Risk Response Plan and the Risk Register is maintained at all times
  Risk Response Plans should be created and maintained by Risk Owners
Risk Documents

## Slide 86: Risk Management Overview
Risk Response Plan
  Typically, a Risk Response Plan will include the following as a minimum:
    Unique Identifier, Risk Description (as described in the Risk Register)
    Pre-Response Probability, Impact, Expected Value & Proximity
    Risk Owner
    Response Plans (who, what, when and where in as much detail as possible)
    Residual Probability, Impact, Expected Value & Proximity
    Cost of Response
Risk Documents

## Slide 87: Risk Management Overview
Risk Progress Report
  May be a separate document or form part of a wider progress report for the organisational activity in question
  Responsibility of the manager of the specific organisational activity (e.g. Operations Manager, Project Manager)
Risk Documents

## Slide 88: Risk Management Overview
Risk Progress Report
  Typically, a Risk Progress Report will include the following as a minimum:
    Trends of overall Risk Exposure
    Numbers and trends of risks emerging within each documented category
    Anticipated new risks that will require management attention
Risk Documents

## Slide 89: Risk Management Overview
Risk Techniques

## Slide 90: Risk Management Overview
There are a number of well-established techniques that can be applied during the Risk Management process
Typically, a technique is best applied at a specific step in the process, though some can be useful at other stages
The tools and techniques used to support Risk Management for a particular organisational activity, should be defined in the Risk Management Strategy for that activity
Risk Techniques

## Slide 91: Risk Management Overview
Stakeholder Analysis
PESTLE Analysis
SWOT Analysis
Prompt List (e.g. Risk Breakdown Structure)
Probability Impact Grid
Summary Risk Profile
Risk Response Planning
Risk Techniques

## Slide 92: Risk Management Overview
Stakeholder Analysis
  Captures who the stakeholders are, their respective roles within the activity and their degree of participation
  Can undercover conflicting interests that need to be managed
  Can identify each stakeholder’s level of influence, their importance in achieving the activity, and the impact of the activity on the stakeholder
  Used primarily during the Identify – Context process step
Risk Techniques

## Slide 93: Risk Management Overview
Stakeholder Analysis – Influence/Interest Matrix
Risk Techniques

## Slide 94: Risk Management Overview
Stakeholder Analysis
  A RACI chart can also be used to assist stakeholder analysis
    Responsible (those who deliver the activity)
    Accountable (those who take credit for success or accountability for failure. Only one person can be Accountable for each activity)
    Consulted (those whose opinions are sought)
    Informed (those who are advised on progress)
Risk Techniques

## Slide 95: Risk Management Overview
Stakeholder Analysis – RACI Chart
Risk Techniques

## Slide 96: Risk Management Overview
PESTLE Analysis
  Aimed at understand aspects of the context of the activity by using the following prompts:
    Political, Economic, Sociological
    Technological, Legal, Environmental
  Can be completed during a team meeting or workshop
  Used primarily during the Identify – Context process step
Risk Techniques

## Slide 97: Risk Management Overview
PESTLE Analysis
Risk Techniques

## Slide 98: Risk Management Overview
SWOT Analysis
  Focuses attention on Strengths, Weaknesses, Opportunities and Threats (identified strengths and weaknesses are a likely source of potential risks)
  Forms a basis for improved understanding of the organisations market position and it’s competition
  Brings together Internal and External analysis
  Most effective when conducted as a group activity
  Can be used in conjunction with PESTLE
  Used during the Identify – Context and Identify – Risks steps
Risk Techniques

## Slide 99: Risk Management Overview
SWOT Analysis
Risk Techniques

## Slide 100: Risk Management Overview
Prompt Lists (Risk Breakdown Structure)
  An organisational activity is broken-down into sub-components
  Each descending level represents an increasingly detailed definition of the sources of risk
  Similar to the Product Breakdown Structure and Work Breakdown Structure techniques used in Project Management
  Used primarily in the Identify – Risks process step
Risk Techniques

## Slide 101: Risk Management Overview
Risk Breakdown
Structure
Risk Techniques

## Slide 102: Risk Management Overview
Probability Impact Grid
  Provides a way of prioritising risks
  Provides a way of defining Risk Tolerance thresholds for a particular organisational activity
  Used in the Assess – Estimate step, but defined (in terms of the scales and rankings to be used) in the Identify – Context step
Risk Techniques

## Slide 103: Risk Management Overview
Probability Impact Grid
Risk Techniques

## Slide 104: Risk Management Overview
Summary Risk Profile
  Provides a visualisation of the total risk posed to an organisational activity by positioning individual risks on a map
  Shows the combined Probability and Impact Assessment
  Incorporate Risk Tolerance threshold, providing the trigger for escalation
  Uses colour-coding to reflect individual risk status
  Must be kept current, and in line with the Risk Register
Risk Techniques

## Slide 105: Risk Management Overview
Summary Risk Profile
Risk Techniques

## Slide 106: Risk Management Overview
Summary Risk Profile
  Risks outside of the Risk Tolerate threshold for the activity must be escalated
  Colour-Code
    White (agreed action cannot begin until a future date)
    Red (no progress made)
    Amber (moderate progress is being made but behind schedule)
    Green (progress made in line with expectation for this stage of the activity)
    Blue (risk response has been successfully implemented)
Risk Techniques

## Slide 107: Risk Management Overview
Risk Response Planning
  Enables a range of response options to be considered from a documented list
  A response should be chosen that provides the maximum possible change to the risk exposure for the least investment
  Response plans are recorded in the Risk Register
  Important to document any residual risk remaining after the implementation of the chosen response
  Important to identify and describe any secondary risks that may be caused by the implementation of the chosen response
Risk Techniques

## Slide 108: Risk Management Overview
Risk Response Planning
  Response Types
    Avoid a Threat / Exploit an Opportunity
    Reduce a Threat / Enhance an Opportunity
    Transfer the Risk
    Share the Risk
    Accept the Risk
    Prepare Contingency Plans
Risk Techniques

## Slide 109: Risk Management Overview
Risk Response Planning
  Response Types - Avoid a Threat / Exploit an Opportunity
    This option is about making the uncertain situation certain by removing the risk, often by removing the cause of the threat or implementing the cause of the opportunity
    In most cases, costs will be incurred in removing the risk the completely, these costs must be therefore be justified
Risk Techniques

## Slide 110: Risk Management Overview
Risk Response Planning
  Response Types – Reduce a Threat / Enhance an Opportunity
    This option is about taking action now to
      change the probability and/or impact of a threat (mitigation) or
      Increase the likelihood and/or impact of an opportunity
    In most cases, costs will be incurred when taking such actions. These costs must therefore be justified against the expected change to the residual risk
Risk Techniques

## Slide 111: Risk Management Overview
Risk Response Planning
  Response Types – Transfer a Risk
    This option is about transferring part of the risk to a third-party (taking out an insurance policy is an example of this)
    Used mainly as a response to Threats rather than Opportunities
    Important to understand that only part of the risk is being transferred (e.g. an insurance policy would cover the cost should the threat actually occur, but the organisation would still be impacted in other areas such as time delay)
    In most cases, costs will be incurred when taking such actions. These costs must therefore be justified against the expected change to the residual risk
Risk Techniques

## Slide 112: Risk Management Overview
Risk Response Planning
  Response Types – Accept the Risk
    This option means that the organisation decides to accept that a risk may occur, and decides to take no action, exposing itself to the full possible impact
    Residual risk is unchanged, but neither are any costs incurred
    An organisation may take such an option with respect to the fluctuation of exchange rates, import duties or other such levies
    This option should not be chosen if the risk expose exceeded the Risk Tolerance for the organisational activity in question
Risk Techniques

## Slide 113: Risk Management Overview
Risk Response Planning
  Response Types – Prepare Contingency Plans
    This option means that the organisation decides to accept that a risk may occur, and decides to take no immediate action, but puts in place a series of contingencies to deal with the impact should it occur
    Sometimes called the ‘fall-back plan’ option as it can be used as a secondary response when the response chosen initially has not resulted in the desired outcome
Risk Techniques

## Slide 114: Risk Management Overview
Risk Health Check

## Slide 115: Risk Management Overview
Used to check the health of current Risk Management practices and identify areas for improvement
Can be a self-assessment, performed internally, or carried-out by a specialist third-party (e.g. auditors)
Can be targeted at specific organisational activities and adapted to the nature of the business
Should be formally administered and follow a four step process of:
  Preparation, Data Collection, Data Analysis, Review & Report
Risk Health Check

## Slide 116: Risk Management Overview
Preparation
  Confirm sponsor
  Define scope and timing of the exercise
  Select a team and brief them on any relevant background information
  Define roles and responsibilities
  Agree the approach and the questions that will be asked
  Define the interview format and schedule the interviews
Risk Health Check

## Slide 117: Risk Management Overview
Data Collection
  Review available documentation and record individual findings
  Carry-out interviews and record in detail
Data Analysis
  Identify and patterns and trends
  Identify strengths and weaknesses
  Focus on key items that need to be addressed
  Conduct intermediate interview with the sponsor
  Identify recommendations
Risk Health Check

## Slide 118: Risk Management Overview
Review and Report
  Draft report
  Conduct final interview with sponsor
  Finalise and submit report
Risk Health Check

## Slide 119: Risk Management Overview
Questions to be asked
  Should be structured into 8 sections, on for each of the Risk Management Principals
  Questions can be quite detailed, but should solicit a simply ‘yes’ or ‘no’ answer in order to make analysis possible.
  Alternative scoring methods can be used (e.g. 1 to 5, or Poor/Average/Good)
  Questions should be asked and answered in an honest, open, and blame-free environment in order to capture the most realistic overall picture
Risk Health Check

## Slide 120: Risk Management Overview
Risk Maturity Model

## Slide 121: Risk Management Overview
Establishes a benchmark for moving forward
Provides the basis for an organisation to measurement the level to which Risk Management has been successfully embedded against a globally used and accepted model (CMM)
Forms the platform for continual incremental improvement over time
Risk Maturity Model

## Slide 122: Risk Management Overview
Usual structure of the model is as a matrix with the following three components
  Levels
  Criteria
  Competency
It is common to use the 8 Risk Management Principals as the Criteria
Risk Maturity Model

## Slide 123: Risk Management Overview
Sample matrix before organisational specific competencies are added
Risk Maturity Model

## Slide 124: Risk Management Overview
5 Levels of Maturity
  Initial
  Repeatable
  Defined
  Managed
  Optimising
Risk Maturity Model

## Slide 125: Risk Management Overview
1st Level of Maturity – Initial
  The organisation undertakes the minimum risk identification and assessment required to satisfy compliance requirements
  Risks are examined only annually
  No definition in place for Risk Tolerance or Risk Appetite
  No formal risk process in place
  Risks that occur are dealt with only in a reactive manner
Risk Maturity Model

## Slide 126: Risk Management Overview
2nd Level of Maturity – Repeatable
  Risk Tolerance and Risk Appetite have been establish
  A risk process has been defined
  A risk profile is in place, providing understanding of the sources of risk that the organisation faces
  The organisation has started to allocate resources to risk-related activities
  Roles and responsibilities are starting to be formally defined
Risk Maturity Model

## Slide 127: Risk Management Overview
3rd Level of Maturity – Defined
  Processes have been further developed and refined
  A dedicated risk management function has been created, co-ordinating effort and ensuring a consistent approach
  Early Warning Indicators are developed
  Response Planning is starting to take shape
  High-level risks are reviewed on a regular basis at board level
Risk Maturity Model

## Slide 128: Risk Management Overview
4th Level of Maturity – Managed
  The culture of Risk Management is being led by the CEO
  Risk Management plays a regular part in key decision-making
  Analysis of risk has become more rigorous, leading to improvement in response planning and implementation
  There is an stronger emphasis on measuring, aggregating and managing risks across the whole organisation
  A dedicated budget for managing risk has been established
Risk Maturity Model

## Slide 129: Risk Management Overview
5th Level of Maturity – Optimising
  The highest level of maturity
  There is now a culture of continual improvement filtered down into all layers of the organisation
  Risk Management policies, processes and resources are fully aligned
  A training and education programme is in place
  Risk Management responsibilities are included in Job Descriptions, Staff Inductions and Staff Appraisals
Risk Maturity Model